## Testing Checklist
S.No | Checklist | Checklist Description | Result | Remarks
| Analyze the business | 1) Understand the business and problem. 2) Application we are developing for the problem
| Storyboards | 1) Storyboards review 2) Analyze the functionality we are implementing in the application 3) If any issues/changes in the Storyboard need to followup for UI team
| Process Flows | 1) Review the Process flows and understand it 2) If any changes updated to the respective implemented user
| ER Diagrams | Review the ER Diagrams
| Functionality & Technical Architecture | 1) Review the Functionality and Technical Architectures 2) Should maintain in Teams for reference, in each and every project
| Execution Plan Document | Should involve in Execution plan document preparation
| Test Plan Document | Prepare Test plan document for the respective application and upload in the Teams
| Checklist | Maintain page wise/role wise related functionlaities (complete breakdown), based on it track the project status
| Test Scenarios & Test Cases (Remodified Testcases) | 1) Need to start the test cases for the application by following the Storyboards 2) BVT and System test cases we should maintain separately 3) UAT test cases
| Review Test Cases | 1) Test cases should be review 2) After review of test cases, share to the Dev team
| Converted HTML pages testing | 1) Compare the Mockup and Converted HTML pages 2) If any issues, log the issues in the TFS and update to the team
| Section 508 testing | 1) For Converted HTML pages, perform the accessbility testing 2) If any issues, log them in the TFS and update to the team
| Compatibility testing | 1) For converted HTML pages perform the compatibility testing Note: Should cover the browsers (IE, Chrome, Mozilla latest versions) 2) Should cover the Screen resolution Maximum: 1920 x 1080 to Minimum: 1024 x 768
| Test environment | Need to know the test environment before the build release Ex: Sharepoint version, Patch, URL path etc…
| Testing site- Deploy build & perform BVT | 1) Deploy the build in the testing site 2) Perform BVT on the latest build 3) BVT should target for UAT 4) If any high priority issues, update to the team and log the issues in the TFS 5) Provide the BVT results and send the BVT status mail
| Deploy build in UAT and test | 1) If BVT is "Pass", deploy the build in the UAT 2) Perform high level testing, to ensure that implemented functionalities are working
Please refer the sheet checklist after build release
| User Manuals | Need to prepare the User Manuals for the respective project
Deployment Document

## BVT Checklist
S.No | Task | Checklist need to refer | Comments | Status Verifed (Yes/No)
1 | Before deployment | 1) Deployment document 2) WSP/.bak file/Incremenatl files 3) Resolved work items sheet 4) Build Notes: a) Implemented Functionalities b) Known issues 5) Executed BVT test cases sheet | 1) If anything as missed in the deployment, contact the Project lead and inform. 2) Based on the oral dicsussion, keep the written mail for the Released build mail. (If still going to continue the BVT)
| After deployment of the new build | Verify the .js and .CSS files are in the Encrypted format
| Build Deployment mail | Provide the build deployment, reply mail to the team | Follow the mail Thread.
| Build Verification Testing Criteria | 1) Implemented functionalities need to test the high level along with complete round of testing on the application. 2) While performing the BVT , parallely test the Resolved work items (High severity items) | Application testing target mostly on the suggested browsers
| BVT results | For Every 2 hours need to provide the BVT results | Upload the excecuted BVT test results in the Teams and Provide the mail to the team by inlcuding Satish sir in the mail.
Provide the BVT Status
| BVT is Passed | 1) If BVT is passed, send the mail with Excecuted BVT test cases along with status and with Resolved work items sheet 2) Prepare the Test Build Plan
| BVT is Failed | 1) If BVT is failed, send the mail status 2) Don't perform any testing on the failed build
After Receving the incremental build follow the above same steps
| BVT is not completed | If BVT is not completed by EOD, provide the status as In progress
Build Pass/Fail Criteria
| BVT = Pass | 1) Implemented functionalities need to work without breakings and requirement need to match 2) In the supporting browsers, application need to work without any blockings.
| BVT = Fail | 1) Any of the implemented functionality is not working as expected 2) Based on the new functional implementation, previous implemented functionalities affected 3) In the Supporting browsers, if functionality is not working 4) Flow breakings and unable to continue for next level role testing.
| BVT=Partially Pass | 1) Implemented functionalities are working but in the least probability scenarios the functionality is not working as expected 2) Usability issues

## Checklist for Build testing
Testing checklist after release of build
Task | Comment
BVT along with Resolved work items
BVT - pass - Deploy in UAT (After confirmation with Satish sir) BVT - Fail - Intimate to Satish sir and report the priority issues
Retesting the Work items (if anything pending) | Based on the Work items, if work items restest is completed move to next task 2) Provide the mail for retested resolved work items (Follow the mail Thread of the build)
Section 508 COMPLIANCE (Titles, Tab order, JAWS Screen reader, Grey scale, Alt attributes) | If completed the work move to next task
System testing- Functional testing (Positive and negative scenarios should cover) and Regression testing & cover the UI and Usability testing.
Non-Functional testing: * Security Testing * Performance Testing * Compatibility Testing * Usability Testing
Performance testing through Automation
Build completion mail | 1) Follow the mail Thread 2) Close the Task in the TFS, which as created while releasing the build
Note: Every end of the day take the backup of the site, if required

## UAT Checklist
S.No | Checklist | Checklist Description | Comments
1 | Before deploying the build, take the Confirmation from Satish sir
2 | Take the backup of the old build | If client performed any actions in the site
3 | Communicate priority issues with the On-Site team before/after drop of the build | Share the priority/Known issues in the UAT deployment mail in detail.
4 | All .js files should be in Encrypted format
5 | Test accounts | 1) Only test accounts should use. 2) In the respective roles, test user names should be constant. (Don't change frequently)
6 | Data | Relevant data should be added in the application
7 | Time Zone | Verify the Time Zone